## decisions
Decision Reference | Description | Responsibility Center | Time Frame | Performance Indicators | Implementation Status | Status / Comments | ImplementationStatusID | id
| The Sectoral Council directed the Secretariat to prepare a comprehensive proposal on the future International Women's day as well as other Regional and International Days such as the International and African Youth Day, the UN Day for Persons with Disabilities, the Day of the African Child at EAC level and table the proposal to the next meeting of the Sectoral Council for consideration. | DSS/PGCD/DHRA | Report to the 2nd Sectoral Council Meeting | Comprehensive proposal on International Women's Day Celebration prepared and considered | 1 | Status / Comments | 1 | 1340
| The Sectoral Council directed the EAC Secretariat to broaden the scope of the Conference thematic areas to include issues which affect children negatively | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Conference thematic areas broadened to include negative paragdim affecting Children | 1 | Status / Comments | 1 | 1339
| The Sectoral Council directed the Secretariat to convene the first meeting of the regional steering committee by the 15th of April 2012 | DHRA/PGCD | 15th April, 2912 | Meeting convened | 1 | Status / Comments | 1 | 1338
| The Sectoral Council directed each Partner States to nominate two experts and constitute the regional steering committee by 15th March 2012 for preparation of the proposed EAC Children's Right Conference | Partner States | 15th March, 2012 | Experts nominated and regional steering committee constituted | 1 | Status / Comments | 1 | 1337
| The Sectoral Council directed the Secretariat to mobilise the necessary resources to facilitate the implementation of the proposed project by June 2014 | DSS/PGCD/DF | June, 2014 | Amount of resources mobilized for the implementation of the project | 1 | Status / Comments | 1 | 1336
| The Sectoral Council directed the Secretariat to ensure that the project addresses the challenges faced by women involved in cross border trade; | DSS/PGCD/DT | Report to the 2nd Sectoral Council Meeting | Challenges faced by women involved in cross border trade addressed | 1 | Status / Comments | 1 | 1335
| The Sectoral Council directed the Secretariat to incorporate the issues of Persons with Disabilities in the design of the Project; | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Issues of Persons with Disabilities incorporated in the Project | 1 | Status / Comments | 1 | 1334
| The Sectoral Council directed the Secretariat to expedite the formulation of the Project on Empowering Border Communities and convene a meeting of experts to consider the zero draft of the project by July 2012 | DSS/PGCD | July, 2012 | Project on Empowering Border Communities expedited and zero draft considered by the Experts | 1 | Status / Comments | 1 | 1333
| The Sectoral Council directed the Secretariat to formulate a policy on promoting women and youth in socio-economic development and women in business by June 2014 | DSS/PGCD | June, 2014 | Policy on promoting women and youth in socio-economic development and women in business formulated | 1 | Status / Comments | 1 | 1332
| The Sectoral Council directed the Secretariat to ensure that the specific recommendations of the conference are referred to the relevant Sectoral Council for action | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Recommendations submitted to the relevant Sectoral Councils | 1 | Status / Comments | 1 | 1331
| The Sectoral Council directed the Secretariat to prepare a matrix of the conference recommendations (Conference on the Role of Women in ¦Socio-Economic Development and Women in Business) indicating clear demarcations of implementation, responsibilities and timeframes for implementation and circulate to Partner States by June 2012. | DSS/PGCD | June, 2012 | Matrix of the conference recommendations developed | 1 | Status / Comments | 1 | 1330
| The Sectoral Council directed the Secretariat to convene a meeting of Experts to formulate the Protocol on Gender equality, youth, children, social protection, social welfare and community development by September 2012 | DSS/PGCD | September, 2012 | Meeting convened Gender equality, youth, children, social protection, social welfare and community development Protocol formulated | 1 | Status / Comments | 1 | 1329
| The Sectoral Council directed the Secretariat to develop a regional roadmap by November 2012 that will guide Partner States to meet the MDGs goals and targets | DSS/PGCD | November, 2012 | Regional roadmap developed in line with the MDGs goals and targets | 1 | Status / Comments | 1 | 1328
| The Sectoral Council directed the Secretariat to develop standardized data collection guidelines for Partner States and circulate to Partner States for input by November 2012 and coordinate the exercise | DSS/PGCD | November, 2012 | Standardized data collection guidelines developed and circulated to Partner States Partner States comments submitted | 1 | Status / Comments | 1 | 1327
| The Sectoral Council directed the Secretariat to finalise the Draft Social Development Framework and presnet the Final Draft Framework for consideration by the 27th Meeting of the EAC Council of Ministers | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Draft Social Development Framework finalized and considered by the 27th Council Meeting | 1 | Status / Comments | 1 | 1326
| The Sectoral Council directed the Partner States in collaboration with the EAC Secretariat to convene national stakeholder consultative forums on the Draft EAC Social Development Framework by June 2012 | DSS/PGCD/Partner States | June, 2012 | National Stakeholder Consultative Forums convened | 1 | Status / Comments | 1 | 1325
| The Sectoral Council directed the Secretariat to expedite the process of establishing the Children, Youth, and EAC Women Council within a period of one year after all Partner States have in place the national Children, Youth and Women Councils. | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Children, Youth and Women Councils established | 1 | Status / Comments | 1 | 1324
| The Sectoral Council directed the Partner States to expedite the establishment of their respective National Children, Youth and Women Councils by 2013 | Partner States | December, 2013 | Partner States National Children, Youth and Women Councils established | 1 | Status / Comments | 1 | 1323
| The Sectoral Council directed the Secretariat to develop guidelines for the establishment of EAC Children, Youth, and Women Councils | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Guidelines for the establishment of EAC Children, Youth, and Women Councils developed | 1 | Status / Comments | 1 | 1322
| The Sectoral Council directed the Secretariat to present the final draft youth policy to the Second Meeting of the Sectoral Council on Gender, Youth, Children, Social Protection and Community Development for consideration by November 2012 | DSS/PGCD | November, 2012 | Final Draft Youth Policy considered | 1 | Status / Comments | 1 | 1321
| The Sectoral Council directed the Secretariat to convene a meeting of experts to review and refine the draft Youth policy | DHRA/PGCD | Report to the 2nd Sectoral Council Meeting | Meeting convened Draft Youth Policy refined | 1 | Status / Comments | 1 | 1320
| The Sectoral Council directed the Secretariat to circulate the draft Youth Policy to Partner States for consultations and inputs | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Draft Youth Policy circulated to Partner States Partner States comments submitted. | 1 | Status / Comments | 1 | 1319
| The Sectoral Council directed the Secretariat to hire a policy development expert to finalize the draft youth policy | DHRA/PGCD | Report to the 2nd Sectoral Council Meeting | Policy development Expert hired Draft Youth Policy finalized | 2 | Status / Comments | 2 | 1318
| The Sectoral Council directed the Secretariat to develop the above policies by 2014 (EAC Children Policy, the EAC Community Development Policy, the EAC Gender Policy and an EAC Social Protection and Social Welfare Policy) | DSS/PGCD | December, 2014 | Policies on EAC Children Policy, the EAC Community Development Policy, the EAC Gender Policy and an EAC Social Protection and Social Welfare Policy developed. | 1 | Status / Comments | 1 | 1317
| The Sectoral Council directed the Secretariat to align the strategic plan to the future policies including the EAC Children Policy, the EAC Community Development Policy, the EAC Gender Policy and an EAC Social Protection and Social Welfare Policy | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | EAC Strategic Plan aligned to future policies | 1 | Status / Comments | 1 | 1316
| The Sectoral Council directed the Secretariat to develop a regional declaration on all forms of Violence Against Women, Children and all other vulnerable groups by june 2014. | DSS/PGCD | June, 2014 | Regional declaration on all forms of Violence Against Women, Children and all other vulnerable groups developed | 1 | Status / Comments | 1 | 1315
| The Sectoral Council recommended the EAC Council to direct the Secretariat to strenghten the human resource capacity of the Department responsible for Gender and Community Development and to ensure that the capacity issues of the department are addressed in the first phase of the on-going Institutional Review process; and also take into account the 18th Council of Mininster Meeting decision which directed the Secretariat to establish a Children and Youth position under existing Administrative Structure. | DHRA/PGCD | Report to the 2nd Sectoral Council Meeting | Human resource capacity of the Department responsible for Gender and Community Development strenghtened. Children and Youth position established. | 2 | Status / Comments | 2 | 1314
EAC/TCM1/DIRECTIVE 6 | The Sectoral Council directed the Secretariat in consultation with the Permanent Secretary of Ministry of Roads in Kenya, Permanent Secretary Ministry of Infrastructure Development in Tanzania and the Chief Executive Officer of TANROADS and other members of the Technical Committee to assess the launch preparations and rehearse the launch on 27th April, 2009. |  | report on 27th April, 2009. | Launch preparations assessed and rehearsed on 27th April , 2009. | 1 | Status / Comments | 1 | 161
EAC/TCM1/DIRECTIVE 5 | The Sectoral Council directed the Secretarait to: i. Include all members of the Council of Ministers and Ministers related to Roads, Transport, Communications and Public Works in the list of invitees i1. Prepare the status of progress of works for briefing purposes on the basis of its regional nature rather than the country status. |  | Report to the next meeting. | Number of influential members included in the list of invites. Status of progress prepared. | 3 | Status / Comments | 3 | 160
EAC/TCM1/DIRECTIVE 4 | The Sectoral Council directed the Secretariat to Avail the draft statements for H.E. President Jakaya Mrisho Kikwete and H.E. President Mwai Kibaki to the United Republic of Tanzania and the Republic of Kenya by 20th April, 2009; | DSG | by 20th April 2009. | Draft statements availed . | 1 | Status / Comments | 1 | 159
EAC/TCM1/DIRECTIVE 3 | The Sectoral Council directed the Secretariat to Convene a meeting of the Technical Committee of the Project to finalize on the preparation activities by 24th April, 2009; | DSG | by 24th April 2009. | Meeting of the Technical Committee convened . | 1 | Status / Comments | 1 | 158
EAC/TCM1/DECISION 1 | The Sectoral Council took note of the work done towards the preparation of the East African Railways Master Plan but noted that there were flaws, and directed the Secretariat in consultation with Partner States to update within three months the Master Plan with current and accurate information and details; | DP | Report with in three month. | Railways Master Plan updated. | 3 | Status / Comments | 3 | 157
EAC/TCM1/DIRECTIVE 2 | The Sectoral Council directed that the prioritization criteria for railways corridors for development take into account among other parameters, linkage of landlocked countries to the maritime ports; existence of a legal framework establishing the Northern and Central Corridor Authorities; inter-linkages between Partner States and linking of the Region to the neighbouring countries; and potential for spurring development especially related to exploitation on natural resources. |  | Report to the next meeting. | Number of Accounts taken in the prioritization criteria. | 2 | Status / Comments | 2 | 156
EAC/TCM1/DIRECTIVE 1 | The Sectoral Council directed the Secretariat in consultation with Partner States to undertake a study on the feasibility of the Public Private Partnerships for infrastructure development in the region including the legal and legislative framework to support the arrangement; | DSG/PSS | Report to the next meeting | Feasibility Study undertaken. | 3 | Status / Comments | 3 | 155