## decisions
Decision Reference | Description | Responsibility Center | Time Frame | Performance Indicators | Implementation Status | Status / Comments | ImplementationStatusID | id
| Directed the Secretary General in consultation with the relevant Heads of State to report regularly on the implementation of decisions including non-compliance and decided that the status of implementation remains a standing item on the Agenda of the Summit. | Secretary General | Continuous | Regular Reports on implementation and non-compliance submitted to the Summit by Secretary General | 1 | Status / Comments | 1 | 99
| The Summit directed the Council of Ministers to study the modalities of including French as a language of the Community in addition to English and Kiswahili. | Council of Ministers/ DSG SS | No timeframe given | Modalities for inclusion of the French as an additional language of the Community studied and recommendations made. | 1 | Status / Comments | 1 | 32
| The Summit noted the justifiable cause for the need to harmonise the terms and conditions of service for the elected members of the East African Legislative Assembly with those of almost equal status within the community. The Summit approved a Lumpsum increment Of USD 1,206 Per member with effect from 1st July 2014. | Secretary General/ Clerk | 1st July 2014 | Lump sum payment of USD 1,206 allocated to all EALA Members effective 1st July, 2014 | 1 | Status / Comments | 1 | 31
| The Summit directed that the internationalized New Generation East African Passport be launched by November 2015. | DSG (PSS) | November 2015 | East African Passport launched by November, 2015 | 2 | Status / Comments | 2 | 30
| The Summit approved the Council recommendation to extend the jurisdiction of the East African Court of Justice to cover trade and investment as well as matters associated with the East African Monetary Union. On Human Rights matters as well as Crimes against Humanity, the Summit directed the Council of Ministers to work with the African Union on This Matter. | CTC/EACJ | Report progress at the 16th Ordinary Summit | EACJ jurisdiction extended to cover trade and investment as well as matters associated with the East African Monetary. Working mechanism established between the EAC and the AU. | 1 | Status / Comments | 1 | 29
| The Council of Ministers apprises the Summit on the progress made on implementation of the roadmap to Single Currency at every Ordinary Summit | DSG P&I | Continuous | Implementation status of the roadmap to Single Currency presented at every Ordinary Summit | 1 | Status / Comments | 1 | 28
| The Council of Ministers develops the Bills for the establishment of the institutions provided in the Protocol for consideration by the East African Legislative Assembly as provided for in the Road Map | Council of Ministers | Report progress at the 16th Summit | No. of Bills developed and considered by EALA No. of Institutions established | 1 | Status / Comments | 1 | 27
| The Summit directed that the following institutions necessary for the implementation of the EAMU be established:-I) The East African Monetary InstituteIi) The East African Statistics Bureau to be responsible for StatisticsIii) The East African Surveillance, Compliance and Enforcement Commission to be responsible for Surveillance, Compliance and Enforcement; and Iv) The East African Financial Services Commission to be responsible for Financial Services. | Secretary General | Report progress at the 16th Summit | The Number of Institutions established for the implementation of the EAMU. | 1 | Status / Comments | 1 | 26
| The Summit directed that Council of Ministers should implement the Roadmap to Single Currency as indicated in the schedule on the EAMU Protocol | Council of Ministers | Report progress at the 16th Summit | Status of implementation of Roadmap to Single Currency. | 1 | Status / Comments | 1 | 25
| The Summit directed that all Partner States should conclude the ratification process of The EAMU Protocol by July, 2014; | Partner States | July, 2014 | No. of Partner States that will have ratified the EAMU Protocol by July, 2014 and deposited instruments of ratification to the Secretary General | 1 | Status / Comments | 1 | 24
| The Summit received the progress report on the Roadmap for the establishment of the East African Federation. The Summit noted that the revised Model Structure, Road Map and Action Plan will be considered by the Council of Ministers and submitted to the 12th Extra-Ordinary Summit Meeting in April 2014. | DSG (PF) | April, 2014 | East African Political Federation revised model structure, road map and action plan considered and presented to the 12th Extra-ordinary Summit Meeting for approval | 1 | Status / Comments | 1 | 23
| The Summit received the progress report on the verification of the Application of the Republic of Somalia to join the East African Community. The Summit noted that the Terms of Reference for the verification process had been developed and a Verification Committee put in place. The Summit directed the Council of Ministers to submit progress report on the verification exercise at the 16th Ordinary Summit in November 2014. | Secretary General | November, 2014 | Progress Report on the verification of the application of the Republic of Somalia presented to the 16th Ordinary Summit in November 2014. | 1 | Status / Comments | 1 | 22
| The Summit received the progress report on the negotiations for the admission of the Republic of South Sudan into the East African Community. the Summit observed that the Council of Ministers had established a High Level Negotiation Team to conduct the negotiations and enable the Summit make a decision on the matter at the 12th Extra-Ordinary Summit in April 2014. | Secretary General | April, 2014 | Report on the Negotiations for the admission of the Republic of South Sudan into the East Africa presented at the 12th Extra-Ordinary Summit in April 2014 | 1 | Status / Comments | 1 | 21
| The Summit received the report on the attainment of the Single Customs Territory. The Summit noted that the framework for the operationalisation of The Single Customs Territory had been finalised and adopted by the Council. the Summit directed that The Single Customs Territory Commences On 1st January 2014 and that all operational requirements be finalised by June 2014. | Partner States | January 1st, 2014 for the Single Customs Territory and June, 2014 for finalization of operational requirements. | Single Customs Territory commencing effective January 1st, 2014 All operational requirements finalised by June, 2014 | 1 | Status / Comments | 1 | 20
| The Summit directed the Council to conclude the EAC Institutional Review and report to the Summit at the 12th Extra-Ordinary Meeting in April 2014. | Council of Ministers | April, 2014 | Institutional Review process concluded and report presented | 1 | Status / Comments | 1 | 19
| The Summit directed the Council to submit progress reports in implementation of major decisions and directives of the Council and the Summit every six months. | Chairperson of Council/SG | Continuous 1st report expected in May/ June 2014 | Progress report in implementation of major decisions and directives of the Council and the Summit presented every six months . | 1 | Status / Comments | 1 | 18
| The Summit directed the Council to present a report on Alternative Financing Mechanism Including the option of 1% of imports from outside the East African Community in Principle of Financial Solidarity and Equity and report to the Summit at its 12th Extra-Ordinary Meeting in April 2014. | Chairperson of Council | April, 2014 | Report on Alternative Financing Mechanism presented for consideration during the 12th Extra-Ordinary Meeting | 1 | Status / Comments | 1 | 17
| The Summit directed the secretariat to prepare a comprehensive list on non implementation of all decisions for consideration at the 12th Extraordinary Summit in April 2014. | Secretariat | April 2014 | A comprehensive list of outstanding Summit Decisions and Directives (1st -15th compiled and presented. | 1 | Status / Comments | 1 | 16
| The Summit undertook to report on individual Partner States’ implementation of decisions involving their respective countries at every Ordinary Summit | Partner States | Annually | Country specific implementation reports presented at every Ordinary Summit meeting | 1 | Status / Comments | 1 | 15
| Directed that the roadmap to the conclusion of the Protocol on the establishment of the East African Community Monetary Union will include holding the following meetings: the third meeting of the Sectoral Council on East African Monetary Union to finalize the technical negotiations; the extraordinary council of ministers to clear the draft protocol on the establishment of the East African Community Monetary Union and refer it to the Sectoral Council on legal and judicial affairs to clear the draft protocol |  | Report to the next meeting | Meetings being held | 1 | Status / Comments | 1 | 33
EAC/CM1/Decision 1 | The Council urged the Partner States to urgently respond to ICAO’s suggested approach in the implementation of the EAC Civil Aviation Safety Project, based on the recommended revised role by the Partner States. | PCI | Report to the next Council | EAC Civil Aviation Safety Project implemented | 1 | Status / Comments | 1 | 1166
EAC/CM1/Decision 10 | The draft EAC Industrial Development Strategy which has been prepared by the Trade Industry and Investment Committee be forwarded by the Secretariat to the Partner States for their study with a view to consideration and adoption by the Council at its next meeting. | SG/CTC | Report to the next Council | Industrial Development Strategy adopted | 1 | Status / Comments | 1 | 1181
EAC/CM1/Decision 11 | urged the Partner States to address the issue of the improvement of air communication through the relevant Sectoral Committee and the Air Transport Facilitation Committee. | DI/Communication | Report to the council | issues addressed | 1 | Status / Comments | 1 | 1182
EAC/CM1/Decision 2 | (i) A Committee on Agriculture and Food Security should be established; (ii) The Committee should comprise representatives from Partner States’ departments for Crops, Livestock, Agicultural Policy and Planning and Fisheries at the level of Directors; (iii) The Committee should have the following Working Groups (at Experts’ level) whose role will be to formulate projects and programmes and discuss any other relevant issues stipulated in the Treaty: - Sanitary and Phyto-sanitary (SPS) Working Group; and - Farm Inputs Working Group. | DPS/PA | Report to the next Council | Existence of Agriculture and Food Security committee | 1 | Status / Comments | 1 | 1167
EAC/CM1/Decision 3 | The East African Medical Research Council (EAMRC) should be revitalised and renamed “the East African Health Research Council (EAHRC)” and covers, in its scope, such wide areas as Health Services including Health Sector reforms, this matter be addressed by the Working Group on Health Research Issues. | PHO | Report to the Next Council | Level of compliance | 1 | Status / Comments | 1 | 1168
EAC/CM1/Decision 4 | The Council decided the Operationalisation of the East African Tourism Council The Secretariat should convene a meeting of this Council after Tanzania’s submission of its nominees. | PTO | Report to the next council | Tanzania nominees submitted and EATC operational | 1 | Status / Comments | 1 | 1171
EAC/CM1/Decision 5 | The Secretariat: (i) should seek views from the East African Aviation Academy, Soroti, Mweka College of Wildlife Management and Kenya Utalii College of Hotel and Tourism Management, on the required revitalisation to the desired level of excellence; (ii) should convene a meeting of the Heads of the three institutions to: - synthesize and rationalise their requirements and come up with a joint document that can be used to solicit necessary funding; - draw an implementation schedule. | PTO | Report to the next Council | necessary consultation made and Implementation schedule drawn | 1 | Status / Comments | 1 | 1172
EAC/CM1/Decision 6 | A Panel of Experts/Hoteliers composed of five members from each Partner State should be formed to develop criteria for the Standardisation and Classification of Hotels, Restaurants and other specialised tourist accommodation facilities within the East African Community. | PTO | Report to the Next Council | Existence of criteria for the Standardisation and Classification of Hotels, Restaurants and other specialised tourist accommodation facilities within the East African Community. | 1 | Status / Comments | 1 | 1173
EAC/CM1/Decision 7 | The Council established a Committee on the Facilitation of Movement of Persons, Immigration, Labour/Employment and Refugees. | PTO | Report to the next council | Committee on the Facilitation of Movement of Persons, Immigration, Labour/Employment and Refugees operationalized | 1 | Status / Comments | 1 | 1174
EAC/CM1/Decision 8 | A competent, strong, independent and autonomous regional authority should be established to implement the Community’s Competition Policy and Law; | SG/CTC | Report to the next Council | regional authority established | 1 | Status / Comments | 1 | 1179
EAC/CM1/Decision 9 | The East African Community Competition Policy and Law should be concluded in tandem with the Protocol on the Establishment of the East African Customs Union; | SG/CTC | Report to the next Council | Competition Policy and Law concluded | 1 | Status / Comments | 1 | 1180
EAC/CM1/Directive 1 | In pursuance of the provisions of Article 118, the Partner States should: - develop a common drug policy; - harmonise drug registration procedures; - strengthen quality control capacities; - harmonise drug regulatory controls for both banned and illicit drugs and develop a common strategy for public drug education; and - develop a common strategy for public drug education and information for the East African Community, including drug advertisement. | PHO | Report to the council | Drug policy harmonised | 1 | Status / Comments | 1 | 1169
EAC/CM1/Directive 2 | Partner States should avail the Secretariat with their respective key health indicators for incorporation into a regional database. | PHO | Report to the next Council | key health indicators availed and incorporated into regional database | 1 | Status / Comments | 1 | 1170
EAC/CM1/Directive 3 | The Council: took note of these activities undertaken to promote the East African Community; and directed the Secretariat to include, in future reports, follow up strategies with regard to some of the more important contacts made; and to disseminate on a timely basis the outcomes of these contacts/meetings to the interested parties. | PIRO | Report to the next Council | Level of Adherence | 1 | Status / Comments | 1 | 1175
EAC/CM1/Directive 4 | The Council: (a) noted, with concern the severe impacts of the recurrent drought and floods on the social and economic development, and on the environment of the Partner States; (b) established a regional Team of Experts to prepare a joint strategy and action plan for monitoring, forecasting and mitigating the impact of drought and floods in the region; the strategy and action plan should be ready within nine months. The regional team of experts should be drawn from the relevant sectors including meteorology, water, environment, energy, health, agriculture and forestry; | DPS/PENR | Report to the next council | action plan for monitoring, forecasting and mitigating the impact of drought and floods in the region prepared and monitored | 1 | Status / Comments | 1 | 1176
EAC/CM1/Directive 5 | urged the Partner States to establish mechanisms for regular exchange of information on matters pertaining to tariff and non- tariff barriers. | DC | Continuous | established mechanisms for regular exchange of information on matters pertaining to tariff and non- tariff barriers. | 1 | Status / Comments | 1 | 1177
EAC/CM1/Directive 6 | An East African Community Competition Policy and Law be developed, the activities of which should be determined by the principle of subsidiarity; the objective of the Competition Policy, which should cover all economic sectors, shall be to ensure, protect and promote free competition; | DC | Report to the next Council | Existence of an East African Community Competition Policy and Law | 1 | Status / Comments | 1 | 1178
EAC/EX/CM 29/Decision 22 | The Council decided to seek an advisory opinion on the issues of “forfeiture” as provided under Article 67 of the Treaty and “compensation” as used under Regulation 96(3) of the EAC Staff Rules and Regulations from the East African Court of Justice | CTC | July 2014 | An Application for Advisory Opinion filed | 1 | Status / Comments | 1 | 269
EAC/EX/CM 29/Decision 18 | The Council adopted the draft EAC Trade Negotiations (repeal) Bill, 2013 and initiated the process of repealing of the East African Trade Negotiations Act, 2008 | CTC/PLD | Sixth Meeting of the 2nd Session of the East African Legislative Assembly | Level of compliance | 1 | Status / Comments | 1 | 268
EAC/EX/CM 29/Decision 17 | The Council adopted the seven Securities Directives | PLD | Immediately | Level of Compliance | 1 | Status / Comments | 1 | 267
EAC/EX/CM 29/Directive 23 | The Council directed the Partner States and the Secretariat to expeditiously implement all the outstanding decisions of the Summit | Partner States/DSG | No deadline given | Number of outstanding decisions implemented | 1 | Status / Comments | 1 | 266
EAC/EX/CM 29/Directive 22 | The Council directed the Secretariat to ensure that the decisions and directives contained in the report of the Summit are always in line with what is contained in the Summit Communique | DSG | Continuous | Level of Compliance | 1 | Status / Comments | 1 | 265
EAC/EX/CM 29/Directive 21 | The Council directed the Secretariat to expedite the preparation of the draft Protocol to operationalize the Extended Jurisdiction of the East African Court of Justice to cover trade and investment and matters associated with the Monetary Union and submit it to the Sectoral Council at its 16th Meeting | PLD | In time for 16th SCLJA Meeting | Draft Protocol prepared and submitted | 1 | Status / Comments | 1 | 264
EAC/EX/CM 29/Decision 21 | The Council referred the draft Protocol on Good Governance to Sectoral Council of Ministers responsible for EAC Affairs to address the matters raised by the Sectoral Council of Legal and Judicial Affairs | PPAO | Next Meeting of SCMREAP | Matters addressed | 1 | Status / Comments | 1 | 263
EAC/EX/CM 29/Decision 20 | The Council referred the entire Draft Protocol on Immunities and Privileges of the East African Community , its Organs and Institutions to the 16th Meeting of the Sectoral Council on Legal and Judicial Affairs for Legal input | CTC | No deadline given | Legal input provided on the Draft Protocol | 1 | Status / Comments | 1 | 262
EAC/EX/CM 29/Decision 19 | The Council revisited its earlier decision referring only Articles 2(Scope), 3(Objectives ) and 11(Institutional Arrangements )of the draft Protocol on Immunities and privileges of the East African Community , its Organs and Institutions to the 16th Meeting of the Sectoral Council on Legal and Judicial Affairs for Legal input | LOS | In time for 16th SCLJA Meeting | Legal input provided on the Draft Protocol | 1 | Status / Comments | 1 | 261
EAC/EX/CM 29/Directive 20 | The Council directed the Secretariat to -(i) re-draft the Protocol on East African Community Regional Cooperation on Health ; )ii) submit to Partner States the draft Protocol on East African Community Regional Cooperation on Health by 2nd May , 2014 ; and (iii) present it to the 16th Meeting of the Sectoral Council on Legal and Judicial Affairs for Legal input | CTC | No deadline given | Protocol re-drafted , submitted and presented | 1 | Status / Comments | 1 | 260
EAC/EX/CM 29/Directive 19 | The Council directed (i) that the current Protocol on The Establishment of the Inter-University Council for East Africa be amended in order to lay a basis for the revision/repeal of the Inter-University Council for East African Act 2009; and thereafter (ii) the Secretariat to thereafter prepare a Bill on the Establishment of the Inter-University Council of East Africa based on the amended Protocol | ES/IUCEA | No deadline given | Protocol amended and a Bill prepared | 1 | Status / Comments | 1 | 259
EAC/EX/CM 29/DIRECTIVE 18 | The Council directed the Partner States to ensure that before Bills passed by the Legislative Assembly are assented by the Heads of State , the Attorneys General are consulted for appropriate Legal Advice | Partner States /EALA | Continuous | Consultations made | 1 | Status / Comments | 1 | 258
EAC/EX/CM 29/Directive 17 | The Council directed Partner States to adopt the Seven Directives and implement them accordingly | Partner States | No deadline given | Number directives that have been adopted and implemented | 1 | Status / Comments | 1 | 257
EAC/EX/CM 29/Directive 16 | The Council directed the Secretariat to initiate the process of filling in the vacant position of Principle Gender and Community Development Officer (P3)from the Republic of Burundi in line with EAC Staff Rules and Regulation so as to finish the remaining employment contract of Mr.Perpetue Miganda's term | DHRA | No deadline given | Process initiated in line with EAC Staff Rules and Regulation | 1 | Status / Comments | 1 | 256
EAC/EX/CM 29/Decision 14 | The Council appointed Ms Roselyn Nyamato Kwenda (Republic of Kenya )who came second best candidate during the interviews with a total score of (82.57) to the position of Senior Librarian (P2) | DHRA | May-14 | Appointment Letter issued and accepted | 1 | Status / Comments | 1 | 255
EAC/EX/CM 29/Directive 15 | The Council directed the Secretariat to always ensure that all recruitment's are based on merit , Subject to Quota System | DHRA | Continuous | Recruitment's based on Merit | 1 | Status / Comments | 1 | 254
EAC/EX/CM 29/Decision 08 | The Council adopted and referred to EALA for debate and approval of a supplementary budget of US$ 147,370 to support implementation of PHE Programme for the FY 2014/2015 | EALA/DF | No deadline given | Supplementary budget debated and approved | 1 | Status / Comments | 1 | 253
EAC/EX/CM 29/Decision 07 | The Council adopted and referred to EALA for debate and approval the additional budget for the FY 2014/2015 a mounting to US$ 1,132,181 to support implementation of the PREPARED and PHE projects activities at the Lake Victoria Basin Commission for the FY 2014/2015 | EALA/DF | No deadline given | Additional Budget debated and approved | 1 | Status / Comments | 1 | 252
EAC/EX/CM 29/Decision 06 | The Council adopted and referred to EALA for debate and approval of additional budget for the FY 2014/2015 a mounting to US$ 388,692 under the EAC Organs and Institutions to cater for the 3% increment of the basic salary for the Financial Year 2013/2014 and funds to be drawn from the Reserve Fund | EALA/DF | No deadline given | Additional Budget debated and approved | 1 | Status / Comments | 1 | 251
EAC/EX/CM 29/Decision 06 | The Council adopted and referred to EALA for debate and approval of additional budget for the FY 2014/2015 a mounting to US$ 388,692 under the EAC Organs and Institutions to cater for the 3% increment of the basic salary for the Financial Year 2013/2014 and funds to be drawn from the Reserve Fund | EALA/DF | No deadline given | Additional Budget debated and approved | 1 | Status / Comments | 1 | 250
EAC/EX/CM 29/Decision 05 | The Council adopted and referred to EALA for debate and approval of additional budget for the FY 2014/2015 a mounting to US$ 2, 748, 942 , funded by contribution from Development Partners | EALA/DF | No deadline given | Additional Budget debated and approved | 1 | Status / Comments | 1 | 249
EAC/EX/CM 29/Decision 04 | The Council adopted and referred to EALA for debate and approval of additional budget for the FY 2014/2015 a mounting US$ 287,150 under the EAC Secretariat, to cater for expenditure for the Election Observer mission to the Republic of Burundi , funded from General Reserve | EALA/DF | No deadline given | Additional Budget debated and approved | 1 | Status / Comments | 1 | 248
EAC/EX/CM 29/Decision 03 | The Council adopted and referred to EALA for debate and approval of additional budget for the FY 2014/2015 a mounting US$ 84,000 under the EAC Secretariat, to cater for expenditure for the Nyerere Centre of Peace and Research, funded from General Reserve | EALA/DF | No deadline given | Additional Budget debated and approved | 1 | Status / Comments | 1 | 247
EAC/EX/CM 29/Directive 14 | The Sectoral Council directed Partner States to carry out sensitization and widely consult with key stakeholders on the Political Federation and report at the 29th Meeting of the Council | Partner States | 29th Meeting of the Council | Number of Partner States that have carried out sensitization and wide consultations with stakeholders | 1 | Status / Comments | 1 | 246
EAC/EX/CM 29/Directive 13 | The Council directed the Secretariat to (i) initiate the process of drafting a constitution for the Political Federation (ii) develop a Road map on what the negotiated constitution making process would involve and report at the 29th Meeting of the Council (iii) make comprehensive evaluation performance on the implementation of the protocol on the establishment of the EAC Customs Union , Common Market and Monetary Union and other Laws of the Community and report at the 29th Meeting of the Council | CTC | 29th Meeting of the Council | Process initiated , a Road map developed , comprehensive evaluation made and reported | 1 | Status / Comments | 1 | 245
EAC/EX/CM 29/Directive 12 | The Council directed the Secretariat to closely coordinate work on institutional review and the modalities on sustainable financing of the East African Community with a view to presenting a Report to the Joint Meeting of the Sectoral Council of Ministers responsible for EAC Affairs and Planning and the Sectoral Council of Ministers of Finance for consideration by 30th July 2014 and thereafter the Council at its 29th Meeting scheduled for August 2014 | DSG(F&A)/DF | 30th July 2014 | Work closely coordinated and report presented | 1 | Status / Comments | 1 | 244
EAC/EX/CM 29/Directive 11 | The Council directed the Secretariat to submit the Report of the Experts to the Sectoral Council of Ministers responsible for EAC Affairs and Planning scheduled for June 2014 and thereafter report to the 29th Meeting of the Council scheduled for August 2014 | DSG(F&A)/DHRA | 29th Meeting of the Council | Report submitted and reported | 1 | Status / Comments | 1 | 243
EAC/EX/CM 29/Directive 10 | The Council directed the Secretariat to fund the Meeting of Experts through internal budgetary reallocation | DSG(F&A)/DF | No deadline given | Meeting funded through internal budgetary reallocation | 1 | Status / Comments | 1 | 242
EAC/EX/CM 29/Directive 09 | The Council directed the Secretariat to convene a Meeting of Experts comprising one Expert per Partner State by early June 2014 | DHRA | Early June 2014 | Meeting convened | 1 | Status / Comments | 1 | 241
EAC/EX/CM 29/Directive 08 | The Council directed Partner States to finalize the consultation and submit the comments to the Secretariat by 30th May 2014 | Partner States | 30th May 2014 | Number of Partner States that have finalized consultations and submitted comments | 1 | Status / Comments | 1 | 240
EAC/EX/CM 29/Directive 07 | The Council directed the Secretariat to prepare a standard format to guide Partner States consultations and circulate it by 15th May 2o14 | DSG(F&A)/DF | 15TH May 2014 | A standard format prepared and circulated | 1 | Status / Comments | 1 | 239
EAC/EX/CM 29/Decision 01 | The Council referred matters on the modalities of sustainable financing of the East African Community to the Sectoral Council of Finance and Economic Affairs to consider the different options highlighting implications and making recommendations for consideration by the Sectoral Council at its 29th Meeting scheduled for August 2014 | DF | 29th Meeting of the Council | Matters considered | 1 | Status / Comments | 1 | 238
EAC/EX/CM 29/Directive 06 | The Council directed the Republic of Kenya , Republic of Uganda and the United Republic of Tanzania to disburse their outstanding contributions towards the Operation Save the Nile Perch Project for the LVFO before the end of June 2014 as they had earlier agreed | Republic of Kenya , Republic of Uganda and the United Republic of Tanzania/LVFO | Before the end of June 2014 | Outstanding contributions disbursed by Republic of Kenya , Republic of Uganda and the United Republic of Tanzania | 1 | Status / Comments | 1 | 237
EAC/EX/CM 29/Directive 05 | The Council directed the Republic of Kenya , Republic of Uganda and the United Republic of Tanzania to disburse their outstanding contributions towards the Budget for the LVFO | Republic of Kenya , Republic of Uganda and the United Republic of Tanzania/LVFO | No deadline given | Outstanding contributions disbursed by Republic of Kenya , Republic of Uganda and the United Republic of Tanzania | 1 | Status / Comments | 1 | 236
EAC/EX/CM 29/Directive 04 | The Council directed the Republic of Burundi, Republic of Uganda and the United Republic of Tanzania to pay arrears towards the Budget for the IUCEA | Republic of Burundi , Republic of Uganda and the United Republic of Tanzania /IUCEA | No deadline given | Arrears paid by the Republic of Burundi, Republic of Uganda and the United Republic of Tanzania | 1 | Status / Comments | 1 | 235
EAC/EX/CM 29/Directive 03 | The Council directed the Republic of Burundi, Republic of Uganda and the United Republic of Tanzania to remit their outstanding contributions towards the Budget of the IUCEA for the Financial Year 2013/2014 | Republic of Burundi , Republic of Uganda and the United Republic of Tanzania /IUCEA | No deadline given | Amount of outstanding contribution remitted by the Republic of Burundi, Republic of Uganda and the United Republic of Tanzania | 1 | Status / Comments | 1 | 234
EAC/EX/CM 29/Directive 02 | The Council directed the Secretariat to always prepare and present comprehensive reports on reciepts and expenditure on Development Partners funds as it does for Partner States contribution for consideration by the Council | DSG(F&A)/DF | Continuous | Number of comprehensive reports prepared , presented and considered | 1 | Status / Comments | 1 | 233
EAC/EX/CM 29/Directive 01 | The Council directed the Republic of Burundi, Republic of Rwanda, the Republic of Uganda and the United Republic of Tanzania to remit their outstanding contributions to wards the Budget for the EAC Organs and LVBC for the Financial Year 2013/2014 | Republic of Burundi , Republic of Rwanda , Republic of Uganda and the United Republic of Tanzania | No deadline set | Amount of outstanding contribution remitted by the Republic of Burundi, Republic of Rwanda , Republic of Uganda and the United Republic of Tanzania | 1 | Status / Comments | 1 | 232
| The Sectoral Council directed the Secretariat to prepare a comprehensive proposal on the future International Women's day as well as other Regional and International Days such as the International and African Youth Day, the UN Day for Persons with Disabilities, the Day of the African Child at EAC level and table the proposal to the next meeting of the Sectoral Council for consideration. | DSS/PGCD/DHRA | Report to the 2nd Sectoral Council Meeting | Comprehensive proposal on International Women's Day Celebration prepared and considered | 1 | Status / Comments | 1 | 1340
| The Sectoral Council directed the EAC Secretariat to broaden the scope of the Conference thematic areas to include issues which affect children negatively | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Conference thematic areas broadened to include negative paragdim affecting Children | 1 | Status / Comments | 1 | 1339
| The Sectoral Council directed the Secretariat to convene the first meeting of the regional steering committee by the 15th of April 2012 | DHRA/PGCD | 15th April, 2912 | Meeting convened | 1 | Status / Comments | 1 | 1338
| The Sectoral Council directed each Partner States to nominate two experts and constitute the regional steering committee by 15th March 2012 for preparation of the proposed EAC Children's Right Conference | Partner States | 15th March, 2012 | Experts nominated and regional steering committee constituted | 1 | Status / Comments | 1 | 1337
| The Sectoral Council directed the Secretariat to mobilise the necessary resources to facilitate the implementation of the proposed project by June 2014 | DSS/PGCD/DF | June, 2014 | Amount of resources mobilized for the implementation of the project | 1 | Status / Comments | 1 | 1336
| The Sectoral Council directed the Secretariat to ensure that the project addresses the challenges faced by women involved in cross border trade; | DSS/PGCD/DT | Report to the 2nd Sectoral Council Meeting | Challenges faced by women involved in cross border trade addressed | 1 | Status / Comments | 1 | 1335
| The Sectoral Council directed the Secretariat to incorporate the issues of Persons with Disabilities in the design of the Project; | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Issues of Persons with Disabilities incorporated in the Project | 1 | Status / Comments | 1 | 1334
| The Sectoral Council directed the Secretariat to expedite the formulation of the Project on Empowering Border Communities and convene a meeting of experts to consider the zero draft of the project by July 2012 | DSS/PGCD | July, 2012 | Project on Empowering Border Communities expedited and zero draft considered by the Experts | 1 | Status / Comments | 1 | 1333
| The Sectoral Council directed the Secretariat to formulate a policy on promoting women and youth in socio-economic development and women in business by June 2014 | DSS/PGCD | June, 2014 | Policy on promoting women and youth in socio-economic development and women in business formulated | 1 | Status / Comments | 1 | 1332
| The Sectoral Council directed the Secretariat to ensure that the specific recommendations of the conference are referred to the relevant Sectoral Council for action | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Recommendations submitted to the relevant Sectoral Councils | 1 | Status / Comments | 1 | 1331
| The Sectoral Council directed the Secretariat to prepare a matrix of the conference recommendations (Conference on the Role of Women in ¦Socio-Economic Development and Women in Business) indicating clear demarcations of implementation, responsibilities and timeframes for implementation and circulate to Partner States by June 2012. | DSS/PGCD | June, 2012 | Matrix of the conference recommendations developed | 1 | Status / Comments | 1 | 1330
| The Sectoral Council directed the Secretariat to convene a meeting of Experts to formulate the Protocol on Gender equality, youth, children, social protection, social welfare and community development by September 2012 | DSS/PGCD | September, 2012 | Meeting convened Gender equality, youth, children, social protection, social welfare and community development Protocol formulated | 1 | Status / Comments | 1 | 1329
| The Sectoral Council directed the Secretariat to develop a regional roadmap by November 2012 that will guide Partner States to meet the MDGs goals and targets | DSS/PGCD | November, 2012 | Regional roadmap developed in line with the MDGs goals and targets | 1 | Status / Comments | 1 | 1328
| The Sectoral Council directed the Secretariat to develop standardized data collection guidelines for Partner States and circulate to Partner States for input by November 2012 and coordinate the exercise | DSS/PGCD | November, 2012 | Standardized data collection guidelines developed and circulated to Partner States Partner States comments submitted | 1 | Status / Comments | 1 | 1327
| The Sectoral Council directed the Secretariat to finalise the Draft Social Development Framework and presnet the Final Draft Framework for consideration by the 27th Meeting of the EAC Council of Ministers | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Draft Social Development Framework finalized and considered by the 27th Council Meeting | 1 | Status / Comments | 1 | 1326
| The Sectoral Council directed the Partner States in collaboration with the EAC Secretariat to convene national stakeholder consultative forums on the Draft EAC Social Development Framework by June 2012 | DSS/PGCD/Partner States | June, 2012 | National Stakeholder Consultative Forums convened | 1 | Status / Comments | 1 | 1325
| The Sectoral Council directed the Secretariat to expedite the process of establishing the Children, Youth, and EAC Women Council within a period of one year after all Partner States have in place the national Children, Youth and Women Councils. | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Children, Youth and Women Councils established | 1 | Status / Comments | 1 | 1324
| The Sectoral Council directed the Partner States to expedite the establishment of their respective National Children, Youth and Women Councils by 2013 | Partner States | December, 2013 | Partner States National Children, Youth and Women Councils established | 1 | Status / Comments | 1 | 1323
| The Sectoral Council directed the Secretariat to develop guidelines for the establishment of EAC Children, Youth, and Women Councils | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Guidelines for the establishment of EAC Children, Youth, and Women Councils developed | 1 | Status / Comments | 1 | 1322
| The Sectoral Council directed the Secretariat to present the final draft youth policy to the Second Meeting of the Sectoral Council on Gender, Youth, Children, Social Protection and Community Development for consideration by November 2012 | DSS/PGCD | November, 2012 | Final Draft Youth Policy considered | 1 | Status / Comments | 1 | 1321
| The Sectoral Council directed the Secretariat to convene a meeting of experts to review and refine the draft Youth policy | DHRA/PGCD | Report to the 2nd Sectoral Council Meeting | Meeting convened Draft Youth Policy refined | 1 | Status / Comments | 1 | 1320
| The Sectoral Council directed the Secretariat to circulate the draft Youth Policy to Partner States for consultations and inputs | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | Draft Youth Policy circulated to Partner States Partner States comments submitted. | 1 | Status / Comments | 1 | 1319
| The Sectoral Council directed the Secretariat to hire a policy development expert to finalize the draft youth policy | DHRA/PGCD | Report to the 2nd Sectoral Council Meeting | Policy development Expert hired Draft Youth Policy finalized | 1 | Status / Comments | 1 | 1318
| The Sectoral Council directed the Secretariat to develop the above policies by 2014 (EAC Children Policy, the EAC Community Development Policy, the EAC Gender Policy and an EAC Social Protection and Social Welfare Policy) | DSS/PGCD | December, 2014 | Policies on EAC Children Policy, the EAC Community Development Policy, the EAC Gender Policy and an EAC Social Protection and Social Welfare Policy developed. | 1 | Status / Comments | 1 | 1317
| The Sectoral Council directed the Secretariat to align the strategic plan to the future policies including the EAC Children Policy, the EAC Community Development Policy, the EAC Gender Policy and an EAC Social Protection and Social Welfare Policy | DSS/PGCD | Report to the 2nd Sectoral Council Meeting | EAC Strategic Plan aligned to future policies | 1 | Status / Comments | 1 | 1316
| The Sectoral Council directed the Secretariat to develop a regional declaration on all forms of Violence Against Women, Children and all other vulnerable groups by june 2014. | DSS/PGCD | June, 2014 | Regional declaration on all forms of Violence Against Women, Children and all other vulnerable groups developed | 1 | Status / Comments | 1 | 1315
| The Sectoral Council recommended the EAC Council to direct the Secretariat to strenghten the human resource capacity of the Department responsible for Gender and Community Development and to ensure that the capacity issues of the department are addressed in the first phase of the on-going Institutional Review process; and also take into account the 18th Council of Mininster Meeting decision which directed the Secretariat to establish a Children and Youth position under existing Administrative Structure. | DHRA/PGCD | Report to the 2nd Sectoral Council Meeting | Human resource capacity of the Department responsible for Gender and Community Development strenghtened. Children and Youth position established. | 1 | Status / Comments | 1 | 1314
EAC/TCM1/DIRECTIVE 6 | The Sectoral Council directed the Secretariat in consultation with the Permanent Secretary of Ministry of Roads in Kenya, Permanent Secretary Ministry of Infrastructure Development in Tanzania and the Chief Executive Officer of TANROADS and other members of the Technical Committee to assess the launch preparations and rehearse the launch on 27th April, 2009. |  | report on 27th April, 2009. | Launch preparations assessed and rehearsed on 27th April , 2009. | 1 | Status / Comments | 1 | 161
EAC/TCM1/DIRECTIVE 5 | The Sectoral Council directed the Secretarait to: i. Include all members of the Council of Ministers and Ministers related to Roads, Transport, Communications and Public Works in the list of invitees i1. Prepare the status of progress of works for briefing purposes on the basis of its regional nature rather than the country status. |  | Report to the next meeting. | Number of influential members included in the list of invites. Status of progress prepared. | 1 | Status / Comments | 1 | 160
EAC/TCM1/DIRECTIVE 4 | The Sectoral Council directed the Secretariat to Avail the draft statements for H.E. President Jakaya Mrisho Kikwete and H.E. President Mwai Kibaki to the United Republic of Tanzania and the Republic of Kenya by 20th April, 2009; | DSG | by 20th April 2009. | Draft statements availed . | 1 | Status / Comments | 1 | 159
EAC/TCM1/DIRECTIVE 3 | The Sectoral Council directed the Secretariat to Convene a meeting of the Technical Committee of the Project to finalize on the preparation activities by 24th April, 2009; | DSG | by 24th April 2009. | Meeting of the Technical Committee convened . | 1 | Status / Comments | 1 | 158
EAC/TCM1/DECISION 1 | The Sectoral Council took note of the work done towards the preparation of the East African Railways Master Plan but noted that there were flaws, and directed the Secretariat in consultation with Partner States to update within three months the Master Plan with current and accurate information and details; | DP | Report with in three month. | Railways Master Plan updated. | 1 | Status / Comments | 1 | 157
EAC/TCM1/DIRECTIVE 2 | The Sectoral Council directed that the prioritization criteria for railways corridors for development take into account among other parameters, linkage of landlocked countries to the maritime ports; existence of a legal framework establishing the Northern and Central Corridor Authorities; inter-linkages between Partner States and linking of the Region to the neighbouring countries; and potential for spurring development especially related to exploitation on natural resources. |  | Report to the next meeting. | Number of Accounts taken in the prioritization criteria. | 1 | Status / Comments | 1 | 156
EAC/TCM1/DIRECTIVE 1 | The Sectoral Council directed the Secretariat in consultation with Partner States to undertake a study on the feasibility of the Public Private Partnerships for infrastructure development in the region including the legal and legislative framework to support the arrangement; | DSG/PSS | Report to the next meeting | Feasibility Study undertaken. | 1 | Status / Comments | 1 | 155