## decisions
Decision Reference | Description | Responsibility Center | Time Frame | Performance Indicators | Implementation Status | Status / Comments | ImplementationStatusID | id
| Directed the Secretary General in consultation with the relevant Heads of State to report regularly on the implementation of decisions including non-compliance and decided that the status of implementation remains a standing item on the Agenda of the Summit. | Secretary General | Continuous | Regular Reports on implementation and non-compliance submitted to the Summit by Secretary General | 1 | Status / Comments | 1 | 99
| The Summit directed the Council of Ministers to study the modalities of including French as a language of the Community in addition to English and Kiswahili. | Council of Ministers/ DSG SS | No timeframe given | Modalities for inclusion of the French as an additional language of the Community studied and recommendations made. | 1 | Status / Comments | 1 | 32
| The Summit noted the justifiable cause for the need to harmonise the terms and conditions of service for the elected members of the East African Legislative Assembly with those of almost equal status within the community. The Summit approved a Lumpsum increment Of USD 1,206 Per member with effect from 1st July 2014. | Secretary General/ Clerk | 1st July 2014 | Lump sum payment of USD 1,206 allocated to all EALA Members effective 1st July, 2014 | 1 | Status / Comments | 1 | 31
| The Summit directed that the internationalized New Generation East African Passport be launched by November 2015. | DSG (PSS) | November 2015 | East African Passport launched by November, 2015 | 2 | Status / Comments | 2 | 30
| The Summit approved the Council recommendation to extend the jurisdiction of the East African Court of Justice to cover trade and investment as well as matters associated with the East African Monetary Union. On Human Rights matters as well as Crimes against Humanity, the Summit directed the Council of Ministers to work with the African Union on This Matter. | CTC/EACJ | Report progress at the 16th Ordinary Summit | EACJ jurisdiction extended to cover trade and investment as well as matters associated with the East African Monetary. Working mechanism established between the EAC and the AU. | 1 | Status / Comments | 1 | 29
| The Council of Ministers apprises the Summit on the progress made on implementation of the roadmap to Single Currency at every Ordinary Summit | DSG P&I | Continuous | Implementation status of the roadmap to Single Currency presented at every Ordinary Summit | 1 | Status / Comments | 1 | 28
| The Council of Ministers develops the Bills for the establishment of the institutions provided in the Protocol for consideration by the East African Legislative Assembly as provided for in the Road Map | Council of Ministers | Report progress at the 16th Summit | No. of Bills developed and considered by EALA No. of Institutions established | 1 | Status / Comments | 1 | 27
| The Summit directed that the following institutions necessary for the implementation of the EAMU be established:-I) The East African Monetary InstituteIi) The East African Statistics Bureau to be responsible for StatisticsIii) The East African Surveillance, Compliance and Enforcement Commission to be responsible for Surveillance, Compliance and Enforcement; and Iv) The East African Financial Services Commission to be responsible for Financial Services. | Secretary General | Report progress at the 16th Summit | The Number of Institutions established for the implementation of the EAMU. | 1 | Status / Comments | 1 | 26
| The Summit directed that Council of Ministers should implement the Roadmap to Single Currency as indicated in the schedule on the EAMU Protocol | Council of Ministers | Report progress at the 16th Summit | Status of implementation of Roadmap to Single Currency. | 1 | Status / Comments | 1 | 25
| The Summit directed that all Partner States should conclude the ratification process of The EAMU Protocol by July, 2014; | Partner States | July, 2014 | No. of Partner States that will have ratified the EAMU Protocol by July, 2014 and deposited instruments of ratification to the Secretary General | 1 | Status / Comments | 1 | 24
| The Summit received the progress report on the Roadmap for the establishment of the East African Federation. The Summit noted that the revised Model Structure, Road Map and Action Plan will be considered by the Council of Ministers and submitted to the 12th Extra-Ordinary Summit Meeting in April 2014. | DSG (PF) | April, 2014 | East African Political Federation revised model structure, road map and action plan considered and presented to the 12th Extra-ordinary Summit Meeting for approval | 1 | Status / Comments | 1 | 23
| The Summit received the progress report on the verification of the Application of the Republic of Somalia to join the East African Community. The Summit noted that the Terms of Reference for the verification process had been developed and a Verification Committee put in place. The Summit directed the Council of Ministers to submit progress report on the verification exercise at the 16th Ordinary Summit in November 2014. | Secretary General | November, 2014 | Progress Report on the verification of the application of the Republic of Somalia presented to the 16th Ordinary Summit in November 2014. | 1 | Status / Comments | 1 | 22
| The Summit received the progress report on the negotiations for the admission of the Republic of South Sudan into the East African Community. the Summit observed that the Council of Ministers had established a High Level Negotiation Team to conduct the negotiations and enable the Summit make a decision on the matter at the 12th Extra-Ordinary Summit in April 2014. | Secretary General | April, 2014 | Report on the Negotiations for the admission of the Republic of South Sudan into the East Africa presented at the 12th Extra-Ordinary Summit in April 2014 | 1 | Status / Comments | 1 | 21
| The Summit received the report on the attainment of the Single Customs Territory. The Summit noted that the framework for the operationalisation of The Single Customs Territory had been finalised and adopted by the Council. the Summit directed that The Single Customs Territory Commences On 1st January 2014 and that all operational requirements be finalised by June 2014. | Partner States | January 1st, 2014 for the Single Customs Territory and June, 2014 for finalization of operational requirements. | Single Customs Territory commencing effective January 1st, 2014 All operational requirements finalised by June, 2014 | 1 | Status / Comments | 1 | 20
| The Summit directed the Council to conclude the EAC Institutional Review and report to the Summit at the 12th Extra-Ordinary Meeting in April 2014. | Council of Ministers | April, 2014 | Institutional Review process concluded and report presented | 1 | Status / Comments | 1 | 19
| The Summit directed the Council to submit progress reports in implementation of major decisions and directives of the Council and the Summit every six months. | Chairperson of Council/SG | Continuous 1st report expected in May/ June 2014 | Progress report in implementation of major decisions and directives of the Council and the Summit presented every six months . | 1 | Status / Comments | 1 | 18
| The Summit directed the Council to present a report on Alternative Financing Mechanism Including the option of 1% of imports from outside the East African Community in Principle of Financial Solidarity and Equity and report to the Summit at its 12th Extra-Ordinary Meeting in April 2014. | Chairperson of Council | April, 2014 | Report on Alternative Financing Mechanism presented for consideration during the 12th Extra-Ordinary Meeting | 1 | Status / Comments | 1 | 17
| The Summit directed the secretariat to prepare a comprehensive list on non implementation of all decisions for consideration at the 12th Extraordinary Summit in April 2014. | Secretariat | April 2014 | A comprehensive list of outstanding Summit Decisions and Directives (1st -15th compiled and presented. | 1 | Status / Comments | 1 | 16
| The Summit undertook to report on individual Partner States’ implementation of decisions involving their respective countries at every Ordinary Summit | Partner States | Annually | Country specific implementation reports presented at every Ordinary Summit meeting | 1 | Status / Comments | 1 | 15